Risk Assessment and Mitigation Plan

Project 2: Banking Transaction System

Milestone 1 – Risk Assessment and Mitigation Plan

1. Purpose

This document identifies, analyzes, and plans responses to the risks that could affect the delivery of the Banking Transaction System: a Java application handling accounts, deposits, withdrawals, and transaction history, together with manual and automated testing and Jira-based test management.

2. Scope

The assessment covers the full project lifecycle: development (OOP, collections, exception handling, file/database handling), testing (manual plans, static testing, Selenium WebDriver, Postman), and reporting in Jira.

3. Risk Assessment Method

Each risk is rated on Probability (P) and Impact (I) using a 1–3 scale (1 = Low, 2 = Medium, 3 = High). Risk Score = P × I.

| Score | Level | Response |
| --- | --- | --- |
| 1–2 | Low | Monitor |
| 3–4 | Medium | Mitigate and track |
| 6–9 | High | Immediate mitigation plan and owner |

4. Risk Register

| ID | Category | Risk | P | I | Score | Level |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Technical | Incorrect balance calculation in deposits/withdrawals | 2 | 3 | 6 | High |
| R2 | Technical | Unhandled invalid transactions (negative amounts, overdraft, non-existent account) | 2 | 3 | 6 | High |
| R3 | Data | Data loss or corruption in file/database storage | 2 | 3 | 6 | High |
| R4 | Data | Database connection or schema issues (MySQL/SQLite) | 2 | 2 | 4 | Medium |
| R5 | Security | Weak validation allowing unauthorized or malformed operations | 2 | 3 | 6 | High |
| R6 | Testing | Incomplete test coverage of edge cases | 3 | 2 | 6 | High |
| R7 | Testing | Unstable Selenium tests (timing, locator changes) | 3 | 2 | 6 | High |
| R8 | Testing | Postman API tests not aligned with backend changes | 2 | 2 | 4 | Medium |
| R9 | Schedule | Tasks underestimated; deadlines missed | 3 | 2 | 6 | High |
| R10 | Team | Unclear roles or member unavailability | 2 | 2 | 4 | Medium |
| R11 | Team | Merge conflicts and inconsistent code between members | 2 | 2 | 4 | Medium |
| R12 | Tools | Jira misuse: bugs not logged or tracked properly | 2 | 1 | 2 | Low |
| R13 | Scope | Scope creep (extra features beyond requirements) | 2 | 2 | 4 | Medium |
| R14 | Environment | Tool or version incompatibility (Java, drivers, browsers) | 2 | 2 | 4 | Medium |

5. Mitigation Plan

| ID | Mitigation (prevention) | Contingency (if it happens) | Owner |
| --- | --- | --- | --- |
| R1 | Unit tests for every transaction type; code review of calculation logic | Fix, retest, and log defect in Jira | Developer |
| R2 | Custom exceptions (e.g., InsufficientFundsException, InvalidAmountException) and input validation | Add missing validation and regression tests | Developer |
| R3 | Use transactions/commits; regular backups of data files | Restore from backup; replay from transaction history | Developer |
| R4 | Set up test DB early; keep a schema script in the repository | Switch to SQLite fallback | Developer |
| R5 | Validate all inputs; restrict operations by account state | Patch and run security-focused test cases | Developer / Tester |
| R6 | Boundary value analysis and equivalence partitioning; review test cases | Add tests for uncovered areas before milestone end | Tester |
| R7 | Explicit waits, stable locators, Page Object Model | Rerun, isolate flaky tests, fix locators | Automation Tester |
| R8 | Keep Postman collections versioned; update with each API change | Update collection and rerun | Tester |
| R9 | Break work into small tasks; weekly progress check; buffer time | Reassign tasks; reduce lower-priority items | Project Manager |
| R10 | Written role assignment; backup owner per task | Redistribute tasks at team meeting | Project Manager |
| R11 | Git branches and pull requests; small frequent commits | Resolve conflicts together; agree on code conventions | All members |
| R12 | Define Jira workflow and bug template; log defects immediately | Update tickets before reporting | Tester |
| R13 | Freeze requirements after approval; changes only by team agreement | Drop or postpone extra features | Project Manager |
| R14 | Document tool versions; use the same setup for all members | Align versions using a shared setup guide | All members |

6. Monitoring and Review

- Review the risk register weekly in the team meeting.

- Update probability, impact, and status as the project progresses.

- Log materialized risks and their resolution in Jira.

- Add newly discovered risks with ID, owner, and mitigation.

7. Risk-Related KPIs

| KPI | Target |
| --- | --- |
| High-level risks with an assigned owner and mitigation | 100% |
| Risk register reviewed on schedule | Weekly |
| Defects traced to a registered risk | Tracked and decreasing |
| Mitigation actions completed on time | ≥ 90% |

8. Assumptions

- Team roles follow the Task Assignment and Roles document.

- Owners listed above are placeholders; replace them with team member names.